## Sheet1
Big Data Analytics Application Project Task List
Project Name |  | Team Lightning
Team Members |  | 1) Alex Spence
2) Carl Barbee
3) Mike Urciuoli
Step | Task | Who | Start Date | End Date | Comments
Data Planning Stage
1 | Identify data sources | All | 6/24/2020 | 6/30/2020
2 | Plan where data will reside | All | 6/24/2020 | 6/30/2020 | • All stored in HDFS
3 | Plan remediation action(s) | All | 6/24/2020 | 6/30/2020 | • System will be setup to generate one pre-defined model. Adjustments to that model will require human interaction.
Data Cleaning and Profiling Stage (Each data source is owned by and processed by one team member - steps 4, 5, 6)
Data Source 1 Processing
4 | Write code to ingest data source 1 (if just a copy operation, please provide the command(s)) | Alex | 7/2/2020 | 7/8/2020 | • "hdfs dfs -put" that data into HDFS
5 | Write code to clean/format (ETL) data source 1 | Alex | 7/2/2020 | 7/8/2020
6 | Write code to profile data source 1 | Alex | 7/2/2020 | 7/8/2020
Data Source 2 Processing
4 | Write code to ingest data source 2 (if just a copy operation, please provide the command(s)) | Mike | 7/2/2020 | 7/8/2020 | • "hdfs dfs -put" that data into HDFS
5 | Write code to clean/format (ETL) data source 2 | Mike | 7/2/2020 | 7/8/2020
6 | Write code to profile data source 2 | Mike | 7/2/2020 | 7/8/2020
Data Source 3 Processing
4 | Write code to ingest data source 3 (if just a copy operation, please provide the command(s)) | Carl | 7/2/2020 | 7/8/2020 | • "hdfs dfs -put" that data into HDFS
5 | Write code to clean/format (ETL) data source 3 | Carl | 7/2/2020 | 7/8/2020
6 | Write code to profile data source 3 | Carl | 7/2/2020 | 7/8/2020
Analytic and Application Development Stage
Develop UI / Visualization | Design the UI / Visualization | Mike | 6/24/2020 | 7/3/2020
| Code the UI / Visualization | Carl | 7/3/2020 | 7/8/2020
| Test the front-end UI / Visualization | Alex | 7/3/2020 | 7/8/2020
Develop Analytic | Design the back-end analytic | Alex | 7/8/2020 | 7/15/2020
| Code the back-end analytic | Mike | 7/8/2020 | 7/15/2020
| Test the back-end analytic code | Carl | 7/8/2020 | 7/15/2020
| Analyze results produced by analytic | Alex | 7/8/2020 | 7/15/2020
| Iterate on the analytic | Carl/Mike | 7/8/2020 | 7/15/2020
Develop Application | Design the applicaton | Carl | 7/15/2020 | 7/22/2020
| Code the applicaton | Alex | 7/15/2020 | 7/22/2020
| Test the applicaton | Mike | 7/15/2020 | 7/22/2020
Final application code due |  | All | - | 7/22/2020
© 2016-2020 Suzanne McIntosh, Cloudera